## Work plan
Haptic glove work plan
Assumes nine weeks with the demo in the first week of December. Change the blue start date and all weeks shift.
Week | Start | Alex | Devyansh | Goal for the week | Milestone | Status
1 | 2026-10-05 | Repo setup, packet definition, fake glove and fake sim scripts | Hand measurements, CAD concept, check RASTIC for parts | Parts ordered, packet frozen |  | Open
2 | 2026-10-12 | Motor current control and encoder read from the ESP32 | Bench rig for one finger: spool, guides, cap | One motor pulls a cable with commanded force |  | Open
3 | 2026-10-19 | MuJoCo scene with hand and object, angle mapping, contact force readout | Base plate and straps v1, wearable for one finger | Sim hand follows a fake glove |  | Open
4 | 2026-10-26 | Close the loop over USB, tune force scaling, add safety limits | Fit and friction fixes on the single finger | Feel a virtual object with one finger | M1 | Open
5 | 2026-11-02 | Three-finger firmware, calibration routine at startup | Three-finger glove v2, wiring harness, power rail | Glove wearable with all three motors |  | Open
6 | 2026-11-09 | Three-finger mapping and grasp tuning in sim | Thumb routing fixes, strain relief | Three-finger grasp with force feedback | M2 | Open
7 | 2026-11-16 | LRA drivers, contact burst and force-to-amplitude mapping | LRAs into the caps, cable management | Vibration on contact | M3 | Open
8 | 2026-11-23 | Stretch: wireless link, local contact model | Stretch: power bank mount, glove v3 | Buffer week (Thanksgiving Nov 26) |  | Open
9 | 2026-11-30 | Latency and force measurements, demo scene | Final assembly, photos, CAD exports to repo | Demo, report, video | M4 | Open
Formulas:
Start = [Start, row above]+7

## Shared and risks
Shared tasks
Task | Note
Ordering in week 1 | Critical path. Nothing in week 2 works without the motors, so order before the design is final.
Integration sessions | Meet with the hardware at the end of weeks 4, 6 and 7, where both sides have to fit.
Report | Split like the work: Alex writes control and sim, partner writes the design section.
Balancing the load | Software side is larger. Partner also takes wiring, power, parts ordering and the week 9 measurements.
Risks
Risk | Why | Fallback
Thumb routing | Hardest mechanical part. | If not working by week 6, drop to index and middle finger and still hit M2.
Force feel | Friction in the guides may hide small forces. | Plan a second iteration of the guides in week 4.
Vibration and wireless | Both depend on earlier milestones being on time. | Cut candidates. M2 alone is a complete project.